## Table 1
MISSION STATEMENT: The two-fold mission of the Unity of Fairfax (UofF) Communications & Marketing Team is 1) to build awareness of Unity of Fairfax and the Unity movement in Northern Virginia and the Metro DC Area through integrated digital, print and broadcast communications and 2) to support best practices in internal communications, particularly those for faith communities. [The plan below illustrates on one of several goals of the UoF 2013-14 communications & marketing plan.]
GOAL: To provide engaging, high-quality welcome materials in an attractive, durable "container" to more visitors
AUDIENCE: Visitors at Sunday worship services
MESSAGE: We value and welcome visitors, and invite them to get to know us and become involved in our community.
STRATEGY: Upgrade the current gift bag of materials to a sleeker, more durable and attractive container
Objectives | Tasks | Owner | Timeline | Due Date/Delivery Date | Outcome | Budget
1. Select the ideal "container" for visitor welcome materials | discuss current gift bag vs.a smaller, two-pocket folder via meeting & emails | Ad hoc group from Communications, Welcome/Worship & New Members Ministries | # weeks | date/date | Ad hoc group consensus that folder is better than a gift bag | n/a
| compare three options - a one color, matte folder with a label; a flat envelope printed with Unity logo; a 4-color, coated folder with Unity logo design | Comm Team Leader presents folder samples and costs to Ad hoc group | # weeks | date/date | Ad hoc group selects the coated, 4-color, Unity branded folder | n/a
| recommend folder with cost information to senior minister; order folders | Comm Team Leader; senior minister; office administrator | # weeks | date/date | folder ordered from Unity Web to Print Store and currently used for welcome materials | cost of initial order and future orders
STRATEGY: Provide visitors with higher quality welcome materials
Objectives | Tasks | Owner | Timeline | Due Date/Delivery Date | Outcome | Budget
1. Update and upgrade new welcome folder contents | editor requests input on welcome materials via email | welcome materials editor (comm team member); ad hoc group (see above); lay ministries council leader; sr. minister; office administrator | # weeks | date/date | improvements in print quality, paper stock, artwork and writing | increased costs for heavier weight paper
| improve accuracy, relevance, attractiveness and opportunities to connect visitors with church community | welcome materials editor | # weeks | date/date | welcome material content complements web site content, provides more lay leader contacts and benefit from professional graphic design | n/a
| seek consensus on edited pieces and final contents via group meeting and email | Ad hoc group | # weeks | date/date | consensus achieved
2. Help ensure uniformity in welcome packet preparation | create a sample welcome folder as a template for office volunteers | Comm Team leader, office administrator, office volunteers | # weeks | date/date | sample created | n/a
STRATEGY: Increase the number of visitors who receive a welcome folder, complete the guest card and are welcomed after the worship service.
objective - Determine an ideal way to offer the welcome folder at the Sunday service and identify visitors after service | meet to brainstorm ideas and seek consensus; follow-up emails | Ad hoc group (see above) | # weeks | date/date | The ad hoc group recommended that ushers encourage visitors to identify themselves during the "visitor welcome" part of the service by standing at the front of the sanctuary with the welcome folders. A highly visible carnation attached to the folder allows greeters to identify visitors after the service. Completed visitor information cards provide data on number of visitors who receive a welcome folder. | n/a